## Project
Project Schedule
Project Name: SuiteCRM
| Project Start Date: 01 feb 2022 |  | 2022-02-01 |  |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead: Dr. Ekata Mehul Shah | [9 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21
Project Guide: Dr. Ekata Mehul Shah | time axis 2022-01-31 to 2022-03-27
WBS | TASK/Module | Name of the person | LEAD | PREDECESSOR | START | DEADLINE | END | DAYS | % DONE | WORK DAYS | time axis 2022-01-31 to 2022-03-27
1 | Overall Analysis
1.01 | SuiteCRM Software App Demo analysis | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-01 | 2022-02-02 | 2022-02-02 | 1 |  | 7
1.02 | Logic Behind The Software Application | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-02 | 2022-02-03 | 2022-02-03 | 1
1.03 | SuiteCRM Software Application Overview | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-04 | 2022-02-05 | 2022-02-05 | 1
1.04 | Software App theme settings | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-06 | 2022-02-07 | 2022-02-06 | 1
1.05 | Server Environment | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-06 | 2022-02-07 | 2022-02-07 | 1
1.06 | Frontend Overview & Analysis | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-06 | 2022-02-07 | 2022-02-08 | 1
1.07 | Backend Overview & Analysis | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-06 | 2022-02-07 | 2022-02-09 | 1
2 | Setup Software
2.01 | Installation of SuiteCRM | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-09 | 2022-02-11 | 2022-02-11 | 3 |  | 9
2.02 | Setup Environment | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-12 | 2022-02-13 | 2022-02-13 | 2
2.03 | Setup Wampserver | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-14 | 2022-02-16 | 2022-02-16 | 3
2.04 | Setup Database Environment | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | 1
2.05 | Login Credentials | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-18 | 2022-02-18 | 2022-02-18 | 1
3 | Working on fields
3.01 | Create Account | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | 1 |  | 2
3.02 | Setup Database | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-20 | 2022-02-20 | 2022-02-20 | 1 |  |  | 2022-03-11: GUI for chatroom(one to one)/testing maintainance of frontend&backend
4 | Page Analyzis
4.01 | Account Page | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-21 | 2022-02-21 | 2022-02-21 | 1 |  | 4
4.02 | Lead Page | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-22 | 2022-02-22 | 2022-02-22 | 1
4.03 | Recruitment Field | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-23 | 2022-02-23 | 2022-02-23 | 1
4.04 | Training Field | Astha mehta/vikas kushwah | Astha mehta/vikas kushwah |  | 2022-02-24 | 2022-02-24 | 2022-02-24 | 1
5 | Create Page
5.01 | Recruitment And its Fields | Astha mehta | Astha mehta |  | 2022-02-25 | 2022-02-26 | 2022-02-26 | 2 |  | 4
5.02 | Training And its Fields | vikas kushwah | vikas kushwah |  | 2022-02-27 | 2022-02-28 | 2022-02-28 | 2